## Sheet1
COST BREAKDOWN
WBS Item | Unit | Cost/Unit | Total | WBS Level 1 Total | % Total
1.1 Perencanaan |  |  |  | 10000000 | 8.333%
1.1.1 Pembentukan tim proyek
Project manager | 1 | 2000000 | 2000000
Quality and Procurement Manager | 1 | 2000000 | 2000000
Administration and Communication Manager | 1 | 2000000 | 2000000
Quality Assurance, Risk dan Project Office Manager | 1 | 2000000 | 2000000
Developer | 1 | 2000000 | 2000000
1.2 Analisis |  |  |  | 5000000 | 4.167%
1.2.1 Analisis Kebutuhan
Project Charter | 1 | 1000000 | 1000000
Ruang Lingkup | 1 | 1000000 | 1000000
Manajemen Kebutuhan | 1 | 1000000 | 1000000
WBS | 1 | 1000000 | 1000000
Manajemen Biaya | 1 | 1000000 | 1000000
1.3 Desain |  |  |  | 8000000 | 6.667%
1.3.1 Pembuatan SKPL
Use case diagram | 1 | 1500000 | 1500000
Class diagram | 1 | 1500000 | 1500000
Data flow diagram | 1 | 1500000 | 1500000
CDM | 1 | 1500000 | 1500000
1.3.2 Pembuatan DPPL
PDM | 1 | 1000000 | 1000000
Pembuatan desain tampilan | 1 | 1000000 | 1000000
Pembuatan desain database | 1 | 1000000 | 1000000
1.4 Implementasi |  |  |  | 93000000 | 77.5%
1.4.1 Front-End
Web page | 5 | 5000000 | 25000000
Responsive | 5 | 5000000 | 25000000
1.4.2 Back-End
Implementasi database | 4 | 5000000 | 20000000
Integrasi Front-end dan Back-end (Controller) | 1 | 5000000 | 5000000
1.4.3 Source Code
Source code | 1 | 10000000 | 10000000
1.4.4 Deployment
Hosting | 1 | 1000000 | 1000000
Domain | 1 | 1000000 | 1000000
Pemeliharaan | 6 | 1000000 | 6000000
1.5 Testing |  |  |  | 2000000 | 1.667%
1.5.1 Testing
Testing calon pengguna | 1 | 1000000 | 1000000
Testing admin | 1 | 1000000 | 1000000
Lain - lain |  |  |  | 2000000 | 1.667%
Biaya cadangan |  |  | 2000000
TOTAL |  |  |  | 120000000 | 100%